## Sheet1
IdentityPOC_ScenarioTwo
Acceptance:- The authorised users will be able to access both applications
User Story | Tasks | Assigned To | Status | # Days
Manual Setup |  |  |  | 1
| Create users in active directory | Aniket | Not Started
| Deploy two web applications | Aniket | Active
| Enable authentication\authorization settings for web app | Aniket | Active
| Test with created user (positive test case) | Aniket | Not Started
| Test with unauthorized user(negative test case) | Aniket | Not Started
Devlopment |  |  |  | 1
| implement static page for web app | Mrunal | Active
| implement login page for web app | Mahuya | Active
| Implement logic for user authentication in web app II | Aniket | Not Started
Automation |  |  |  | 2
| create automation for deployment process | Aniket | Not Started
| ARM template for web app | Aniket | Not Started
| Create powershell script to create active directory application | Aniket | Not Started
| Create powershell script to create users in active directory | Aniket | Not Started
Testing |  |  |  | 1
| create demo(Test positive and negative test case) | Aniket | Not Started
| document demo steps and update wiki | Aniket | Not Started