## Sheet1
Identity POC-scenario one
Acceptace Criteria->Authrozied NBME employee will able to login to web app
User Story | Tasks | AssignedTo | Status | # Days | Status
Manual Setup |  |  |  | 1 | Not Started
| Create users in active directory | Shraddha | Not Started |  | Active
| Deploy web application | Shraddha | Not Started |  | Closed
| Enable authentication\authorization settings for web app | Shraddha | Not Started
| Test with created user (positive test case) | Shraddha | Not Started
| Test with unauthorized user(negative test case) | Shraddha | Not Started
Automation |  |  |  | 1
| create automation for deployment process | Shraddha | Not Started
| ARM template for web app | Shraddha | Not Started
| Create powershell script to create active directory application | Shraddha | Not Started
| Create powershell script to create users in active directory | Shraddha | Not Started
Development |  |  |  | 2
| implement static page for web app | Mrunal | Active
| implement login page for web app | Mrunal | Not Started
| Implement logic for user authentication | Shraddha | Active
Testing |  |  |  | 1
| create demo(Test positive and negative test case) | shraddha | Not Started
| document demo steps and update wiki | shraddha | Not Started